RISE TECHNOLOGIES LLC
Technology Procurement Hub Framework
Version 2.0 - Cost-Plus Pricing Model

| Version: | 2.0 - Cost-Plus Model |
| --- | --- |
| Date: | January 2026 |
| Classification: | Internal - Strategic |
| Owner: | NH IT Department |
| Status: | Draft for Review |

# EXECUTIVE SUMMARY

This framework establishes RISE Technologies LLC as the centralized technology procurement hub for NH Group under a Cost-Plus Pricing Model. RISE will manage vendor relationships, process purchase orders, and handle payment flows between entities and technology suppliers, earning a fixed percentage markup on all transactions.

## Key Changes from V1.0

Cost-Plus pricing model (Base Cost + Fixed Markup %)

Entity-initiated requirements with PO flow through RISE

Technology-specific expertise onboarding with 1-month advance notice

Exclusive procurement mandate for approved technologies

Direct PO issuance from RISE to vendors with entity delivery details

# 1. OPERATIONAL MODEL

## 1.1 Cost-Plus Pricing Structure

Pricing Formula: Total Entity Cost = Vendor Base Cost + (Vendor Base Cost × Markup %)

| Vendor Base Cost | Actual invoice amount from vendor to RISE |
| --- | --- |
| Markup Percentage | Fixed agreed percentage (5-15%, negotiated annually) |
| Total Entity Cost | Base Cost + Markup (invoiced by RISE to entity) |
| Transparency | RISE provides vendor invoice copies upon request |

### Example Transaction:

| Vendor Invoice to RISE: | AED 100,000 |
| --- | --- |
| Agreed Markup: | 10% |
| Markup Amount: | AED 10,000 |
| RISE Invoice to Entity: | AED 110,000 |

## 1.2 Procurement Flow

The procurement process follows a six-step flow:

1. Entity to RISE: Submits requirement (product specs, quantity, delivery address, timeline)

2. RISE to Vendor: Issues PO (Bill To: RISE, Ship To: Entity name & address)

3. Vendor to Entity: Delivers to entity address, invoices RISE with base cost

4. RISE to Vendor: Pays vendor per agreed payment terms

5. RISE to Entity: Invoices entity (Base Cost + Markup %, attaches vendor invoice)

6. Entity to RISE: Pays RISE per NH standard payment terms (30 days)

## 1.3 Technology Expertise Onboarding

### Initial Technology Portfolio Definition

Each entity must notify RISE of all technology categories:

Entity completes Technology Portfolio Form

RISE evaluates each category for expertise

RISE responds: Confirmed / Onboarding Required / Not Viable

Both parties agree on final approved list

### Example Technology Categories:

| Category | Examples | Complexity |
| --- | --- | --- |
| Cloud Services | AWS, Azure, Google Cloud | High |
| Enterprise Software | Oracle, SAP, Microsoft | High |
| Security Solutions | Firewalls, EDR, SIEM | High |
| Collaboration | Microsoft 365, Zoom | Medium |
| Hardware | Dell, HP, Lenovo | Medium |
| Telecom Services | Etisalat, du, VOIP | Low |

### New Technology Addition - 1 Month Advance Notice

| Timeline | Activity |
| --- | --- |
| Week 1 | Entity submits New Technology Request |
| Week 1-2 | RISE assesses complexity, expertise needs |
| Week 3 | RISE responds: Approved / Conditional / Declined |
| Week 4 - Month 1 | RISE onboarding: training, vendor setup |
| Month 1+ | Technology goes live for procurement |

Emergency Exception: Entity may procure directly for critical needs with immediate post-notification

## 1.4 Exclusive Procurement Mandate

CRITICAL RULE: Once Technology is Approved for an Entity

RISE becomes the ONLY authorized vendor for that technology

Entity MUST route ALL procurement through RISE

Applies to: purchases, renewals, upgrades, services, maintenance, training

Enforcement: Procurement systems block direct POs

Exceptions require Group CIO + Entity CEO approval

Rationale:

Ensures RISE can negotiate volume discounts

Maintains consolidated vendor relationships

Prevents fragmentation of procurement power

Enables accurate spend tracking

# 2. ENTITY RESPONSIBILITIES

## 2.1 Initial Setup (First Month)

Submit Technology Portfolio Notification

Provide vendor relationships and historical spend data

Document internal approval workflows

Assign RISE liaisons (primary, technical, finance)

Configure systems to route technologies through RISE

## 2.2 Ongoing Responsibilities

| Frequency | Activities |
| --- | --- |
| Monthly | Review invoices (5 days) Process payments (30 days) |
| Quarterly | Cost review Verify markup calculations |
| Annually | Spend analysis Markup renegotiation |

# 3. RISE RESPONSIBILITIES

## 3.1 Service Level Commitments

| Request Type | Response SLA | Resolution SLA |
| --- | --- | --- |
| Emergency | 4 hours | 24 hours |
| Urgent | 1 business day | 2 business days |
| Standard | 2 business days | 5 business days |
| New Technology | 5 business days | 30 days |

Accuracy Commitments:

PO Accuracy: 98%

Invoice Accuracy: 99%

On-Time Delivery: 95%

# 4. FINANCIAL CONTROLS & AUDIT RIGHTS

## 4.1 NH Group Audit Rights

Request vendor invoice copies anytime (24-hour response)

Conduct quarterly cost audits

Annual comprehensive financial audit

Random spot checks (10% monthly)

Verify markup calculations

## 4.2 Prohibited Practices

RISE MAY NOT:

Accept vendor kickbacks without disclosure

Charge fees beyond agreed markup

Inflate vendor costs

Steer toward higher-cost vendors

Misrepresent pricing

Bundle unwanted products

Penalties:

1st violation: Warning + markup -2% (6 months)

2nd violation: Markup -5% (12 months)

3rd violation: Termination + legal action

# 5. 3-PHASE EVALUATION FRAMEWORK

## Phase 1: Initial Assessment (Months 1-2)

Objective: Assess RISE capability to operate cost-plus model

Passing Score: ≥75/100

Week 1-2: Technology portfolio assessment

Week 3-4: Pilot 5-10 transactions

Week 5-6: Review and audit

Week 7-8: Evaluation report to Steering Committee

## Phase 2: Probation (Months 3-8)

Monthly KPIs (all must meet targets):

Response Time SLA: ≥90%

PO Accuracy: ≥95%

Invoice Accuracy: ≥98%

On-Time Delivery: ≥90%

Cost Competitiveness: ≤Market

Transparency: 100%

End Decision (Month 8):

Score ≥80/100 required

Entity satisfaction ≥4/5 required

Pass → Phase 3 | Fail → Extend or Terminate

## Phase 3: Permanent Engagement (Month 9+)

| Frequency | Activities |
| --- | --- |
| Monthly | Performance dashboard 10% invoice spot check |
| Quarterly | Business review KPI scorecard Cost audit |
| Annually | Full audit Markup renegotiation Renewal decision |

# 6. GOVERNANCE STRUCTURE

## 6.1 Steering Committee

Composition:

Group CIO (Chair)

Group CFO

NH IT Manager

Entity representatives

Decision Authority:

Phase transition approvals

Markup adjustments

Dispute resolution

Termination decisions

# 7. EXIT STRATEGY & TERMINATION

## 7.1 Termination Rights

For Cause (Immediate):

SLA <75% for 2 months

Financial misconduct

Security breach

Fraud

For Convenience (90-day notice):

After Phase 1/2 if criteria not met

After Phase 3 anytime

Annual renewal decision

## 7.2 Transition (90 Days)

Days 1-30: Planning and documentation

Days 31-60: Knowledge transfer

Days 61-90: Final handover

NH Always Retains:

All vendor relationships

All contracts

All data

Direct vendor access

# 8. APPENDICES

## Appendix A: Technology Portfolio Form

| Category | Current Vendor | Annual Spend | Complexity | Requirements |
| --- | --- | --- | --- | --- |
| Example: Cloud AWS | AWS Direct | AED 500K | High | RI support needed |

# 9. APPROVAL & SIGNATURES

| Prepared By: | NH IT Manager |
| --- | --- |
| Name: | _________________________________ |
| Signature: | _________________________________ |
| Date: | _________________________________ |

| Approved By: | Group CEO |
| --- | --- |
| Name: | _________________________________ |
| Signature: | _________________________________ |
| Date: | _________________________________ |

END OF FRAMEWORK DOCUMENT

Next Review Date: Q4 2026