RISE Technologies LLC

Technology Hub Framework

Strategic Evaluation & Engagement Model for NH Group

| Version: | 1.0 |
| --- | --- |
| Date: | January 2026 |
| Classification: | Internal - Strategic |
| Owner: | NH IT Department |
| Prepared for: | National Holding PJSC |

Abu Dhabi, United Arab Emirates

TABLE OF CONTENTS

EXECUTIVE SUMMARY	3

1. PROPOSED OPERATING MODEL	4

1.1 Overview	4

1.2 Three-Phase Approach	4

2. PHASE 1: INITIAL ASSESSMENT (Months 1-2)	5

2.1 Objectives	5

2.2 Assessment Dimensions	6

2.3 Scoring & Decision Gate	7

3. PHASE 2: PROBATION PERIOD (Months 3-8)	9

3.1 Probation Structure	9

3.2 Service Level Agreements	10

3.3 Monthly Checkpoints	11

4. PHASE 3: PERMANENT ENGAGEMENT (Month 9+)	12

4.1 Transition to Permanent Status	12

4.2 Enhanced SLAs	13

4.3 Governance Structure	14

5. TERMINATION & EXIT STRATEGY	15

5.1 Exit Triggers	15

5.2 Exit Process	16

6. GOVERNANCE & OVERSIGHT	18

6.1 Steering Committee	18

6.2 Working Groups	19

7. RISK MANAGEMENT	20

7.1 Risk Register	20

8. SUCCESS CRITERIA & DECISION FRAMEWORK	22

9. IMPLEMENTATION ROADMAP	23

10. COMMUNICATION PLAN	25

11. CONCLUSION & NEXT STEPS	26

DOCUMENT CONTROL & APPROVALS	27

# Executive Summary

This framework establishes a structured, risk-mitigated approach for evaluating RISE Technologies LLC's potential role as the centralized technology procurement and service management hub for NH Group entities. The framework implements a phased approach with clear go/no-go decision gates, objective performance criteria, and defined exit strategies to protect NH Group interests.

### Key Principles

- Evidence-based evaluation before commitment

- Probationary period with strict SLA monitoring

- Performance-based continuation with quarterly reviews

- Clear exit strategy with no financial penalty to NH

- Protection of entity autonomy and operational continuity

### Three-Phase Approach

| Phase | Duration | Objective | Decision Gate |
| --- | --- | --- | --- |
| 1. Initial Assessment | Month 1 | Determine minimum viable capability | GO/NO-GO (≥70% score required) |
| 2. Probation | Months 2-7 | Controlled pilot with limited scope | Graduate/Terminate (≥90% SLA required) |
| 3. Permanent Engagement | Ongoing | Full-scale operations with monitoring | Quarterly reviews with termination option |

# 1. Proposed Operating Model

### 1.1 RISE's Intended Role

As Technology Hub, RISE would:

- Act as single point of contact for all NH entities' technology needs

- Source technology solutions, products, and services from market vendors

- Manage vendor relationships, contracts, and negotiations

- Handle AMC (Annual Maintenance Contracts), renewals, and escalations

- Coordinate technical support and service delivery

- Process all technology procurement through RISE (Entity → RISE → Vendor)

Revenue Model:

- Commission on initial software/product/service acquisition

- Annual commission on AMC and maintenance contracts

- Service fee for contract management and vendor coordination

### 1.2 Value Proposition (If Successful)

Potential Benefits:

- Centralized vendor management and negotiation power

- Standardized procurement processes across group

- Consolidated contract management

- Single escalation point for technical issues

- Potential cost savings through volume negotiations

Potential Risks:

- Additional bureaucratic layer slowing decision-making

- Lack of technical expertise to evaluate solutions

- Poor vendor management impacting service delivery

- Entity dissatisfaction with centralized model

- RISE becoming bottleneck for critical technology needs

# 2. Phase 1: Initial Capability Assessment (Month 1)

### Objective

Determine if RISE has minimum viable capability to proceed to probation.

### 2.1 Evaluation Dimensions

A. Organizational Capability (25% weight)

| Criteria | Minimum Requirement | Evaluation Method |
| --- | --- | --- |
| Team Structure | Dedicated team of minimum 5 FTEs | Org chart review, team interviews |
| Technical Expertise | At least 2 team members with IT/technology background | Resume review, technical assessment |
| Vendor Management | Documented vendor management process | Process documentation review |
| Contract Management | Experience managing 10+ technology contracts | Portfolio review |
| Financial Capacity | Ability to handle payment cycles and vendor credits | Financial statement review |

B. Process Maturity (30% weight)

| Criteria | Minimum Requirement | Evaluation Method |
| --- | --- | --- |
| Procurement Process | Documented end-to-end procurement workflow | Process walkthrough |
| SLA Management | Framework for tracking and enforcing vendor SLAs | SLA tracking demonstration |
| Escalation Process | Clear escalation matrix for technical issues | Process documentation |
| Reporting | Monthly reporting capability to stakeholders | Sample report review |
| Risk Management | Vendor risk assessment methodology | Methodology review |

C. Technology Infrastructure (20% weight)

| Criteria | Minimum Requirement | Evaluation Method |
| --- | --- | --- |
| Contract Management System | CRM or contract management platform | System demonstration |
| Ticketing System | Service request tracking system | System access and review |
| Communication Platform | Structured communication with entities and vendors | Platform demonstration |
| Documentation Repository | Centralized document management | Repository access |

D. Domain Knowledge (25% weight)

| Criteria | Evaluation Area | Assessment Method |
| --- | --- | --- |
| ERP Systems | Understanding of Oracle, SAP ecosystems | Technical interview |
| Cybersecurity | Knowledge of security tools and compliance | Security assessment |
| Cloud Services | Azure, AWS experience | Reference checks |
| Data & AI | Understanding of data platforms and AI tools | Technical discussion |
| Industry-Specific Tech | Knowledge of FMCG, Education, Industrial tech | Case study review |

### 2.2 Evaluation Process

Week 1: Information Gathering

- RISE submits capability statement

- Provide organizational structure and team credentials

- Submit process documentation

- Share current vendor portfolio and contracts managed

Week 2: On-site Assessment

- NH IT team conducts 2-day assessment at RISE facility

- Team interviews and technical assessments

- System demonstrations

- Process walkthroughs

Week 3: Reference Checks & Analysis

- Contact current RISE clients (if any)

- Validate vendor relationships

- Check financial stability

- Analyze capability gaps

Week 4: Decision Gate 1

GO Criteria (ALL must be met):

- Minimum team of 5 FTEs with relevant experience ✓

- At least 2 technically qualified team members ✓

- Documented procurement and SLA management processes ✓

- Contract management system in place ✓

- Passing score (≥70%) on domain knowledge assessment ✓

- No major financial red flags ✓

| Category | Weight | Minimum Score |
| --- | --- | --- |
| Organizational Capability | 25% | 60% |
| Process Maturity | 30% | 70% |
| Technology Infrastructure | 20% | 60% |
| Domain Knowledge | 25% | 65% |
| Overall | 100% | ≥70% |

### Decision Outcomes

| Outcome | Actions |
| --- | --- |
| NO-GO (<70%) | • Formal notification to RISE GM • Recommendation: RISE focuses on capability building for 6-12 months • NH entities continue direct vendor management • Re-evaluation option after capability improvement period |
| GO (≥70%) | • Proceed to Phase 2: 6-Month Probation • Sign Probationary Service Agreement • Define pilot scope and KPIs |

# 3. Phase 2: Probationary Period (Months 2-7)

### 3.1 Probation Structure

Duration: 6 months

Scope: Limited pilot with controlled risk

- Start with 2-3 specific technology categories only (e.g., IT hardware, SaaS subscriptions)

- Maximum 2 entities participating initially (recommend starting with smaller entities)

- Transaction value cap: Maximum AED 500K per transaction

- Exclude mission-critical systems during probation

Progressive Expansion:

- Month 2-3: Limited scope, close supervision

- Month 4-5: Expand categories if performance acceptable

- Month 6-7: Full assessment and decision on permanent engagement

### 3.2 Probationary Service Agreement - Key Terms

- No Exclusivity: Entities retain right to direct vendor engagement if RISE fails to deliver

- Performance Security: RISE provides bank guarantee or performance bond

- Payment Terms:

  - Commission paid only after successful delivery and entity acceptance

  - 30-day payment terms after entity confirms satisfaction

  - Withheld amounts if SLAs breached

- Termination Rights:

  - NH can terminate with immediate effect for material breach

  - 30-day notice for convenience termination

  - No penalty to NH for termination

- Data & Contract Ownership:

  - All contracts remain NH property

  - Full handover obligation upon termination

  - RISE has no claim on vendor relationships

### 3.3 Service Level Agreements (SLAs)

A. Response & Resolution Times

| Service Type | Acknowledgment | Resolution Target | Escalation Trigger |
| --- | --- | --- | --- |
| Critical (Production down) | 1 hour | 4 hours | 2 hours |
| High (Major impairment) | 4 hours | 24 hours | 8 hours |
| Medium (Minor issue) | 8 hours | 72 hours | 48 hours |
| Low (Request/query) | 24 hours | 5 business days | 3 business days |
| Procurement Request | 24 hours | 15 business days | 10 business days |

B. Procurement Performance SLAs

| Metric | Target | Measurement | Consequence of Breach |
| --- | --- | --- | --- |
| Quotation Turnaround | 5 business days | From request to 3 vendor quotes | Delay penalty: -5% commission |
| Purchase Order Processing | 2 business days | From entity approval to vendor PO | Delay penalty: -5% commission |
| Delivery Coordination | 100% on-time | Vendor commitments met | Late delivery: No commission |
| Cost Competitiveness | Within 5% of market | Quarterly benchmark | Excess cost: RISE absorbs difference |
| Invoice Accuracy | 98% | Error-free invoicing | Re-work at RISE cost |

C. Vendor Management SLAs

| Metric | Target | Measurement |
| --- | --- | --- |
| Vendor SLA Compliance | 95% | Vendors meet their SLAs |
| AMC Renewal Timeline | 60 days before expiry | Proactive renewal management |
| Escalation Resolution | 85% within SLA | Vendor issues resolved |
| Contract Documentation | 100% | All contracts properly documented and accessible |
| Monthly Reporting | 100% on-time | Reports delivered by 5th of each month |

D. Quality & Satisfaction Metrics

| Metric | Target | Measurement Method |
| --- | --- | --- |
| Entity Satisfaction Score | ≥4.0/5.0 | Monthly survey |
| First-Time Resolution Rate | ≥80% | Ticket analysis |
| Vendor Performance Score | ≥4.0/5.0 | Quarterly vendor scorecard |
| Cost Savings Delivered | ≥5% vs. direct procurement | Quarterly benchmark |
| Process Compliance | 100% | Audit findings |

### 3.4 Monitoring & Reporting

Weekly:

- RISE submits activity log (all requests, status, issues)

- NH IT reviews and flags concerns

Monthly:

- RISE submits comprehensive performance report:

  - SLA compliance scorecard

  - Active procurements status

  - Vendor performance summary

  - Cost savings analysis

  - Issues log and resolution status

- NH IT conducts performance review meeting

- Entity feedback collection

Quarterly:

- Formal performance assessment against all KPIs

- Entity satisfaction survey

- Cost-benefit analysis

- Go/No-Go decision for continuation

### 3.5 Decision Gates During Probation

Month 3 Review (Mid-Probation Checkpoint)

Minimum Performance Criteria:

- SLA compliance ≥80% across all categories

- Entity satisfaction ≥3.5/5.0

- No critical breaches (production impact)

- Zero financial irregularities

Outcomes:

| Outcome | Actions |
| --- | --- |
| Pass | Continue probation, consider scope expansion |
| Conditional Pass | Continue with corrective action plan, no scope expansion |
| Fail | Immediate termination, transition to direct entity management |

Month 6 Review (End of Probation)

Graduation Criteria (ALL must be met):

- SLA compliance ≥90% across all categories ✓

- Entity satisfaction ≥4.0/5.0 ✓

- Cost savings demonstrated ≥3% vs. direct procurement ✓

- Zero critical breaches ✓

- All vendor contracts properly documented and accessible ✓

- Successful handling of at least 10 procurement transactions ✓

- Successful management of at least 5 vendor relationships ✓

Outcomes:

| Outcome | Actions |
| --- | --- |
| Pass | Graduate to Phase 3 (Permanent Engagement with Monitoring) |
| Fail | Terminate engagement, execute transition plan |

# 4. Phase 3: Permanent Engagement with Ongoing Monitoring

### 4.1 Permanent Service Agreement Terms

Scope Expansion:

- Gradual expansion to all technology categories

- Phased onboarding of all NH entities

- Full vendor portfolio transition over 12 months

Commission Structure:

| Service Type | Commission Rate | Payment Terms |
| --- | --- | --- |
| New Software/Product Acquisition | 5-8% (based on value tier) | After delivery & entity acceptance |
| Annual Maintenance Contracts | 3-5% annually | After AMC renewal & payment |
| Professional Services | 5% | After service completion |
| Cloud Services (monthly) | 3% | Monthly after entity payment |

Performance Incentives:

- +1% commission if quarterly satisfaction ≥4.5/5.0

- +2% commission if cost savings ≥10% vs. market

- Bonus pool for exceptional vendor negotiations

Performance Penalties:

- -25% commission for SLA breaches

- -50% commission for critical incidents caused by RISE

- No commission if cost exceeds market by >5%

### 4.2 Ongoing SLA Requirements

Enhanced SLAs (Post-Probation):

| Metric | Target | Review Frequency |
| --- | --- | --- |
| Overall SLA Compliance | ≥95% | Monthly |
| Entity Satisfaction | ≥4.2/5.0 | Quarterly |
| Vendor SLA Compliance | ≥95% | Monthly |
| Cost Competitiveness | Within market ±3% | Quarterly benchmark |
| Procurement Cycle Time | ≤15 business days | Monthly |
| Contract Renewal Rate | ≥95% on-time | Quarterly |
| Incident Escalation | ≥90% resolved within SLA | Monthly |

### 4.3 Quarterly Business Reviews

Agenda:

- Performance scorecard review (all KPIs)

- Entity feedback analysis

- Vendor portfolio health assessment

- Cost savings analysis

- Market benchmark comparison

- Strategic initiatives and improvements

- Issues and corrective actions

- Next quarter commitments

Attendees:

- NH Group CIO (Group CIO)

- NH IT Management

- RISE GM and Operations Head

- Entity IT Representatives (rotating)

Outcomes:

- Performance rating (Exceeds/Meets/Below Expectations)

- Action items and improvement plans

- Decision on continuation/modification/termination

### 4.4 Annual Performance Assessment

Comprehensive Review:

- Full year SLA compliance analysis

- Financial performance (cost savings, commission value)

- Entity satisfaction trend analysis

- Vendor relationship health

- Strategic value delivered

- Market competitiveness assessment

Renewal Decision:

| Performance Rating | Decision |
| --- | --- |
| Exceeds Expectations | Automatic renewal with potential scope expansion |
| Meets Expectations | Renewal with existing terms |
| Below Expectations | Conditional renewal with performance improvement plan OR termination |

# 5. Termination & Exit Strategy

### 5.1 Termination Triggers

Immediate Termination (Material Breach):

- Fraud or financial irregularities

- Data breach or security incident caused by RISE negligence

- Repeated critical SLA breaches (3+ in a quarter)

- Entity satisfaction <3.0/5.0 for 2 consecutive quarters

- Vendor mismanagement causing significant business impact

- Failure to provide required reporting for 2 consecutive months

- Bankruptcy or financial instability of RISE

Termination with Notice:

- Consistent underperformance (SLA compliance <85% for 2 consecutive quarters)

- Entity dissatisfaction (satisfaction <3.5/5.0 for 3 consecutive quarters)

- Cost escalation (>10% above market for 2 consecutive quarters)

- Strategic decision by NH to change operating model

- RISE requests to exit

Notice Periods:

| Termination Type | Notice Period |
| --- | --- |
| Material Breach | Immediate (0 days) |
| Performance-Based | 90 days |
| Convenience | 180 days |
| RISE-Initiated | 180 days |

### 5.2 Transition & Handover Process

Immediate Actions (Day 1-7):

- RISE stops accepting new procurement requests

- Active procurements transferred to NH IT or entity management

- Vendor notification of change in contract management

- Access to all systems and documentation provided to NH

Transition Period (Days 8-90):

Week 1-2: Documentation Handover

- Complete contract repository transfer

- Vendor contact database with relationship history

- Active procurement pipeline with full status

- AMC schedule with renewal dates

- Outstanding issues log with resolution plans

- Financial reconciliation (pending commissions, vendor credits)

Week 3-4: Vendor Relationship Transition

- Joint meetings with all key vendors

- Transfer of relationship ownership to entities/NH IT

- Update vendor records with new contact points

- Transfer of all vendor portals and access credentials

Week 5-8: Entity-by-Entity Handover

For each entity:

- Complete list of active contracts

- Vendor relationship maps

- Outstanding service requests

- AMC schedule and renewal process

- Entity-specific documentation

- Transition meeting with entity IT team

Week 9-12: Knowledge Transfer & Closure

- Final documentation review

- Knowledge transfer sessions with NH IT

- Final financial settlement

- Contract termination formalities

- Post-termination support agreement (if applicable)

### 5.3 Financial Settlement

Principles:

- RISE entitled to commission only for successfully completed work

- No commission on incomplete or failed procurements

- NH withholds final payment until complete handover verified

- Disputes resolved through pre-agreed arbitration

Settlement Calculation:

| Item | Treatment |
| --- | --- |
| Completed Deliveries | Full commission paid |
| In-Progress Procurements | Pro-rated commission based on completion % |
| Failed/Cancelled Projects | No commission |
| AMC Already Paid | Pro-rated commission for service period |
| Future AMC | No commission; transferred to entity/NH |
| Handover Quality | 10-20% of final payment contingent on complete handover |

Holdback:

- NH retains 20% of final settlement for 90 days post-termination

- Released after verification of complete handover

- Adjusted for any post-termination issues discovered

# 6. Governance & Oversight

### 6.1 Governance Structure

RISE Technology Hub Steering Committee

Composition:

- Chair: NH Group CIO (Group CIO)

- Members:

  - NH IT Manager

  - RISE GM

  - 2 Entity IT Representatives (rotating quarterly)

  - NH CFO Representative (for financial oversight)

Frequency: Monthly during probation, Quarterly post-probation

Responsibilities:

- Review performance against KPIs

- Approve significant technology investments (>AED 500K)

- Resolve escalated issues

- Approve changes to framework or SLAs

- Make go/no-go decisions at gates

### 6.2 Working-Level Coordination

RISE-NH IT Interface Team

NH Side:

- IT Manager as primary contact

- Technical leads for specific domains (ERP, Security, Infrastructure)

RISE Side:

- Dedicated Account Manager for NH Group

- Technical specialists as needed

Weekly Sync:

- Active requests status

- Upcoming procurements

- Vendor issues

- Process improvements

### 6.3 Entity Engagement

Entity Autonomy Protection:

- Entities retain right to escalate to NH IT if unsatisfied with RISE

- Critical/urgent requests can bypass RISE with NH IT approval

- Entity IT representatives participate in quarterly reviews

- Annual entity satisfaction survey with results shared

### 6.4 Audit & Compliance

Internal Audit Rights:

- NH reserves right to audit RISE processes quarterly

- Full access to RISE systems, documentation, vendor communications

- Financial audit of commission calculations

- Compliance with NH procurement policies

Vendor Audit:

- RISE must support NH audits of vendor performance

- Provide all documentation for vendor compliance verification

# 7. Risk Management

### 7.1 Risk Register

| Risk | Impact | Mitigation | Contingency |
| --- | --- | --- | --- |
| RISE lacks technical expertise | High | Thorough initial assessment; require technical hires | Fail at Phase 1; do not proceed |
| RISE becomes bureaucratic bottleneck | High | Strict SLA monitoring; bypass mechanism | Termination; direct entity management |
| Vendor relationship damage | Medium | Joint vendor meetings; gradual transition | NH IT direct intervention |
| Cost escalation vs. direct | Medium | Quarterly benchmarking; market comparison | Renegotiate commission or terminate |
| RISE financial instability | High | Financial checks; performance bond | Immediate termination; rapid transition |
| Poor vendor management | High | Vendor scorecards; NH oversight | NH IT takes over vendor relationship |
| Entity dissatisfaction | Medium | Regular feedback; entity representation | Entity exemption or full termination |
| Data/security breach | Critical | Security audit; compliance requirements | Immediate termination; legal action |

### 7.2 Continuous Risk Monitoring

Monthly Risk Assessment:

- Review risk indicators (SLA trends, satisfaction scores, financial metrics)

- Update risk register

- Implement additional controls if needed

Escalation Protocol:

- Yellow Flag: 2 consecutive months of underperformance → Corrective action plan

- Red Flag: Critical breach or 3 consecutive months underperformance → Termination consideration

# 8. Success Criteria & Decision Framework

### 8.1 Overall Success Metrics

For RISE to be considered successful long-term:

Financial:

- Demonstrated cost savings ≥5% vs. direct procurement (verified annually)

- Commission costs justified by value delivered

- No cost overruns attributable to RISE

Operational:

- SLA compliance ≥95% sustained over 12 months

- Entity satisfaction ≥4.2/5.0 sustained over 12 months

- Vendor performance maintained or improved vs. baseline

- Procurement cycle time ≤15 days average

Strategic:

- Standardization achieved across entities

- Vendor consolidation and negotiation power demonstrated

- NH IT time freed up from tactical vendor management

- Scalability proven (handles growing volume without degradation)

### 8.2 Decision Framework Summary

| Phase/Checkpoint | Timing | Decision Criteria | Outcomes |
| --- | --- | --- | --- |
| Phase 1: Initial Assessment | Month 1 | Capability score ≥70% | GO: Proceed to Probation NO-GO: Reject; improvement period |
| Phase 2: Mid-Probation | Month 3 | SLA ≥80%, Satisfaction ≥3.5 | PASS: Continue CONDITIONAL: Corrective plan FAIL: Terminate |
| Phase 2: End of Probation | Month 7 | All graduation criteria met (SLA ≥90%, Satisfaction ≥4.0) | GRADUATE: Permanent FAIL: Terminate |
| Phase 3: Quarterly Reviews | Ongoing | All targets met/exceeded | EXCEEDS: Continue MEETS: Continue BELOW: Plan or terminate |
| Phase 3: Annual Review | Annually | Overall performance satisfactory | RENEW: Another year TERMINATE: Exit process |

# 9. Implementation Roadmap

### Month 1: Initial Assessment

| Week | Activities |
| --- | --- |
| Week 1 | RISE submits capability documentation |
| Week 2 | NH IT conducts on-site assessment |
| Week 3 | Reference checks and analysis |
| Week 4 | Decision Gate 1 - GO/NO-GO for probation |

### Month 2-7: Probation Period

| Month | Key Activities |
| --- | --- |
| Month 2 | • Sign Probationary Service Agreement • Define pilot scope (2 categories, 2 entities) • Baseline current state • RISE setup and onboarding |
| Month 3 | • Mid-probation checkpoint • Review SLAs and entity feedback • Decision: Continue/Corrective Action/Terminate |
| Month 4-6 | • Expand scope if performance acceptable • Continuous monitoring and weekly reviews • Monthly performance reports |
| Month 7 | • Final probation assessment • Decision Gate 2 - GRADUATE/TERMINATE • If graduate: negotiate permanent agreement |

### Month 8-19: Permanent Engagement Ramp-Up

| Period | Key Activities |
| --- | --- |
| Month 8-10 | • Expand to all technology categories (phased) • Onboard additional entities (one per month) • Transition existing vendor relationships |
| Month 11-13 | • First quarterly business review • Full entity portfolio onboarded • Optimize processes based on learnings |
| Month 14-19 | • Steady-state operations • Continuous improvement • Second and third quarterly reviews • Prepare for annual assessment |

### Month 20: First Annual Review

- Comprehensive performance evaluation

- Renewal decision

- Adjust terms if needed for Year 2

# 10. Communication Plan

### 10.1 Stakeholder Communication

To RISE:

- Clear expectations document with this framework

- Regular feedback (weekly during probation, monthly thereafter)

- Transparent performance scoring

- Early warning of concerns

To Entities:

- Introduction of RISE model and benefits

- Pilot scope communication

- Regular updates on RISE performance

- Feedback channels

To Vendors:

- Gradual notification of RISE as interface

- Joint introductions and relationship transfer

- Clear escalation paths maintained

### 10.2 Reporting

| Frequency | Report | Audience |
| --- | --- | --- |
| Weekly (During Probation) | Activity and status report | RISE → NH IT |
| Monthly | Performance report Summary to entities | RISE → Steering Committee NH IT → Entities |
| Quarterly | Performance review and recommendations | Steering Committee → CEO/Board |
| Annually | Comprehensive performance assessment | Steering Committee → Board |

# 11. Conclusion & Next Steps

### 11.1 Framework Benefits

For NH Group:

- Risk-mitigated approach with clear exit strategy

- Objective performance criteria

- Protection of entity interests and operational continuity

- Potential benefits if RISE succeeds, minimal risk if they fail

For RISE:

- Clear expectations and success criteria

- Opportunity to prove value in controlled environment

- Pathway to significant long-term business if successful

### 11.2 Immediate Next Steps

| Step | Timing | Actions |
| --- | --- | --- |
| 1 | Week 1 | NH IT to review and approve this framework |
| 2 | Week 1 | Present framework to CEO/Group CIO for approval |
| 3 | Week 2 | Conduct initial meeting with RISE GM to explain framework |
| 4 | Week 2-3 | RISE submits capability documentation |
| 5 | Week 3-4 | NH IT conducts Phase 1 assessment |
| 6 | End of Week 4 | Decision Gate 1 |
| 7 | If GO: Month 2 | Begin probation |

### 11.3 Critical Success Factors

For this framework to succeed:

- NH IT must commit resources to proper oversight and monitoring

- RISE must commit to transparency and accept performance-based model

- Entities must be engaged and provide honest feedback

- Steering Committee must meet regularly and make timely decisions

- Metrics must be tracked rigorously with no exceptions

### 11.4 Framework Owner & Reviews

Framework Owner: NH IT Manager

Framework Review Schedule:

- After probation (Month 7): Adjust based on lessons learned

- After first year (Month 20): Comprehensive review and update

- Annually thereafter: Review and adjust as needed

# Document Control

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | Jan 2026 | NH IT | Initial framework |

### Approvals

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| NH IT Manager | NH IT Manager |  |  |
| Group CIO | Group CIO |  |  |
| CEO |  |  |  |

This framework provides a comprehensive, risk-mitigated approach to evaluating and potentially engaging RISE Technologies LLC as NH Group's technology hub. All phases include clear go/no-go decision points, objective performance criteria, and defined exit strategies to protect NH Group's interests while giving RISE a fair opportunity to prove their value.